## START HERE
PCB Tracker — fill these in
Work through the sheets in this order. Everything else is calculated or filled by the dashboard.
| Step | Sheet | What to do
| 1 | CLIENTS | List every customer once. The name you type here is what appears everywhere else, so settle the naming now — change it later and old rows will not match.
| 2 | EMPLOYEES | Your team. The "Name in sheet" column is the short name people actually type as a stage owner. Get this right or the People tab cannot attribute work.
| 3 | LISTS | Statuses, reasons and stage names. Already filled — only edit if you want different wording.
| 4 | ACTIVE | One row per board still in progress. Fill Customer, Board, Manager, then each stage: Owner, Status, EDC. Leave EDA until the stage finishes.
| 5 | COMPLETED | Boards where every stage is done. Same columns. You can leave this empty and let the dashboard move boards here as they close.
| 6 | — | Publish the dashboard. From then on the team fills everything through it and these sheets update themselves.
Rules worth knowing
- Cream-coloured cells are yours to fill. White cells with formulas calculate themselves — do not type over them.
- A stage marked NA is not part of that board. It is hidden from the dashboard and excluded from the completion percentage.
- EDC is the expected date of completion. EDA is the actual one. The dashboard writes EDA when someone presses Review done.
- Overall Status decides which sheet a board belongs on. The dashboard reads it back after every save and moves the row.
- Stage owners may combine two people with " + ", for example "Samudra + Sandhya". Both are matched against EMPLOYEES.

## CLIENTS
Clients
One row per customer. The Client name column feeds every dropdown in the tracker.
| Client name | Short code | Sector / domain | Account owner | Status | Notes
| TRS |  |  | Rajesh | Active | 16 boards migrated from the old tracker
| Internal |  |  | Prithvi | Active | 15 boards migrated from the old tracker
| Voila Tech |  |  | Rajesh | Active | 12 boards migrated from the old tracker
| Aerx Labs |  |  | Rajesh | Active | 4 boards migrated from the old tracker
| FLC |  |  | Rajesh | Active | 4 boards migrated from the old tracker
| GMR |  |  | Srinivas | Active | 3 boards migrated from the old tracker
| HAL |  |  | Srinivas L | Active | 3 boards migrated from the old tracker
| RCI |  |  | Srinivas L | Active | 3 boards migrated from the old tracker
| ZMD |  |  | Kiran | Active | 3 boards migrated from the old tracker
| Qernel.AI |  |  | Kranthi | Active | 2 boards migrated from the old tracker
| Unassigned |  |  |  | Active | 2 boards migrated from the old tracker

## EMPLOYEES
Employees
Your roster, pre-filled from what you sent. "Name in sheet" is the short name typed into stage Owner cells — it is the join the People tab depends on.
| Employee code | Full name | Function | Experience (yrs) | Billing | Name in sheet | Projects | Plan | Active?
|  | Srinivasa Rao Supuri | Hardware | 14 | Billed | Srinivas | Aerx Labs, Internal, Qernel.AI, ZMD |  | Yes
| VC_124 | Galipothu Sunil Kumar | Hardware | 18 | Billed | Sunil | Aerx Labs, FLC, GMR, Internal, ZMD |  | Yes
| VC_176 | Jampani Samudralankaiah | Hardware | 6.4 | Billed | Samudra | Aerx Labs, FLC, Internal, ZMD |  | Yes
| VC_183 | Varimadla Anjaneyulu | Hardware | 8.1 | Billed | Anji | FLC, GMR, Internal |  | Yes
| VC_224 | Chintha Vivek Sai | Hardware | 0.1 | Billed | Vivek | Aerx Labs, FLC, GMR, HAL, Internal, TRS, Voila Tech, ZMD |  | Yes
| VC_161 | Veeresh Meeniga | Hardware | 2.7 | Billed | Veeresh | FLC, Internal |  | Yes
| VC_141 | Ravada Ramesh | Hardware | 4.2 | Billed | Ramesh | HAL, TRS |  | Yes
| VC_163 | Ruka Nandi Vardhan Reddy | Hardware | 2.7 | Billed | Vardhan | GMR, TRS, Voila Tech, ZMD |  | Yes
| VC_196 | Keerthi Sepana | Hardware | 1.3 | Billed | Keerthi | GMR, RCI, TRS, Voila Tech |  | Yes
| VC_200 | Harika Kunduru | Hardware | 4 | Billed | Harika | Internal |  | Yes
| VC_229 | Bommi Sandhya | Hardware |  |  | Sandhya | Internal, Voila Tech, ZMD |  | Yes
|  | Naveen | Hardware |  |  | Naveen | HAL, Internal, TRS, Voila Tech |  | Yes
|  | Rajesh | Hardware |  |  | Rajesh Sir | ZMD |  | Yes
| Fabrication vendors | Listed separately so fab work is never counted as someone's workload.
PCB Power
JLC
Micropack

## PROCESS DEFINITION
Process definition
Seven stages, four columns each: Owner, Status, EDC, EDA.
| Stage | Stage name | Completed when | Owner column holds
| S1 | Schematic Design | Schematic released and netlist handed to layout. | A design engineer
| S2 | PCB Layout / Design | DRC and DFM clean, Gerber released. | A layout engineer
| S3 | SI & PI Simulation | All in-scope interfaces within margin and report shared. | A simulation engineer
| S4 | Bare-PCB Fabrication | Bare boards received and inspected. | The fabricator, not a staff member
| S5 | Assembly | Board populated and inspected. | A hardware engineer
| S6 | Bring-up | Board powers up, passes validation and is handed over. | A hardware engineer
| S7 | BOM Procurement | Parts sourced, or alternates agreed. | A design engineer
Column contract the dashboard depends on
- The field header row must contain "Project / Board", with the stage group headers in the row directly above.
- Each stage group header must keep its name — SCHEMATIC, PCB LAYOUT, SI & PI, BARE-PCB FAB, ASSEMBLY, BRING-UP, BOM PROCUREMENT. The S<n> prefix is ignored.
- Within a stage block the order is Owner, Status, EDC, EDA.
- Owner values must match the "Name in sheet" column on EMPLOYEES. Two people combine with " + ".
- Customer values must match the Client name column on CLIENTS.

## ACTIVE
ACTIVE / PENDING BOARDS
One row per board still in progress. Fill the cream cells; the white ones calculate. EDC is the expected date of completion, EDA the actual one.
RESPIN QUEUE | [6 empty] | 1 board(s) flagged for respin
# | Customer | Board | Re-entry Stage | Respin Reason | Raised On | Pull in and start at
1 | Unassigned | USB_Radio-Card |  |  |  | Re-entry stage not set
2
3
4
5
6
7
8
PROJECT |  |  |  | PROCESS ROLL-UP | [6 empty] | S1 SCHEMATIC |  |  |  |  | S2 PCB LAYOUT |  |  |  |  | S3 SI & PI |  |  |  |  | S4 BARE-PCB FAB |  |  |  |  | S5 ASSEMBLY |  |  |  |  | S6 BRING-UP |  |  |  |  | S7 BOM PROCUREMENT |  |  |  |  | RESPIN ORIGIN |  |  |  | FOLLOW-UP
S.No | Customer | Project / Board | Project Manager | Current Stage | Overall Status | EDC (current stage) | Days | Stages Done | Stages In Scope | % Complete | Owner | Status | EDC | EDA | Comment | Owner | Status | EDC | EDA | Comment | Owner | Status | EDC | EDA | Comment | Fabricator | Status | EDC | EDA | Comment | Owner | Status | EDC | EDA | Comment | Owner | Status | EDC | EDA | Comment | Owner | Status | EDC | EDA | Comment | Rev / Respin No. | Re-entered At | Respin Reason | Raised On | Hold / delay reason | Reason check | Notes / Data Check
1 | Aerx Labs | Belly Camera | Prithvi | S1 Schematic | In Progress | 2026-09-08 | 4 days left | 0 | 5 | 0% | Samudra | In Progress | 2026-09-08 |  | Schematic in progress | Srinivas | Not Started |  |  |  |  | Not Started |  |  |  |  | Not Started |  |  |  |  | Not Started |  |  |  |  | NA |  |  |  |  | NA | [8 empty] | Reason not given
2 | Aerx Labs | PVC_CC_V2 / PVCC_V2 | Rajesh | S3 SI & PI | In Progress | Not added | No date set | 2 | 3 | 66.67% | Samudra | Completed |  |  |  | Sunil | Completed | 2026-07-28 |  |  | Vivek | In Progress |  |  | Received the updated file, completed the simulations shared the review. Crosstalk issues were still there; shared with the layout team for modifications |  | NA |  |  |  |  | NA |  |  |  |  | NA |  |  |  |  | NA | [9 empty] | PCB "PVC_CC_V2" + SI&PI "PVCC_V2_Board" merged
3 | FLC | MKB_LITE_FHHL | Rajesh | S3 SI & PI | On Hold | Not added | No date set | 2 | 5 | 40% | Veeresh | Completed | 2026-05-15 |  |  | Veeresh + Samudra | Completed |  |  |  | Vivek | On Hold |  |  | Performed the SI & PI for the DDR, PCIe_RC and DC_DROP and AC anlaysis. EP_PCIe Interface is pending due to crosstalk and return loss issues at the edge finger. |  | On Hold |  |  |  |  | On Hold |  |  |  |  | NA |  |  |  |  | NA | [8 empty] | Reason not given
4 | HAL | CITAR Module Design | Srinivas L | S1 Schematic | Not Started | Not added | No date set | 0 | 5 | 0% |  | Not Started |  |  | Schematic in progress | Ramesh | Not Started | 2026-09-11 |  |  |  | Not Started |  |  |  |  | Not Started |  |  |  |  | Not Started |  |  |  |  | NA |  |  |  |  | NA
5 | Internal | NETRA_NT98566_CAMERA_MODULE | Prithvi | S2 PCB Layout | In Progress | 2026-09-13 | 9 days left | 1 | 5 | 20% | Sandhya | Completed |  |  |  | Sunil | In Progress | 2026-09-13 |  | Component footprint verification in progress |  | Not Started |  |  |  |  | Not Started |  |  |  |  | Not Started |  |  |  |  | NA |  |  |  |  | NA | [8 empty] | Reason not given
6 | Internal | Netra_NXP_SOM_Board | Prithvi | S3 SI & PI | In Progress | Not added | No date set | 2 | 5 | 40% | Samudra + Sandhya | Completed | 2026-07-21 |  |  | Srinivas | Completed | 2026-09-08 |  |  |  | In Progress |  |  | Routing completed,Need the updated schematic as per the review modifications. |  | Not Started |  |  |  |  | Not Started |  |  |  |  | NA |  |  |  |  | NA | [9 empty] | Schematic row = Compulab replacement variant. SI&PI "NXP_SOM" (ZMD) kept separate — confirm if same board
7 | Internal | Netra_POE_Plus(MP8008) | Prithvi | S1 Schematic | On Hold | Not added | No date set | 0 | 4 | 0% |  | On Hold |  |  | ZYNQ Module for RF Camera prioritized | Naveen | On Hold | 2026-08-19 |  |  |  | On Hold |  |  |  |  | On Hold |  |  |  |  | NA |  |  |  |  | NA |  |  |  |  | NA | [8 empty] | Reason not given | Blank on upload, set to NA: S6 Assembly. Confirm NA vs Not Started.
8 | Internal | Netra_RZ/V2N_SOM (Renesas) | Prithvi | S2 PCB Layout | In Progress | 2026-09-25 | 21 days left | 1 | 5 | 20% | Veeresh + Samudra | Completed | 2026-09-04 |  |  | Srinivas | In Progress | 2026-09-25 |  | Placement is in progress. The component sizes need to be changed in the schematic. I have informed Veeresh and am waiting for the updated schematic. |  | Not Started |  |  |  |  | Not Started |  |  |  |  | Not Started |  |  |  |  | NA |  |  |  |  | NA | [8 empty] | Reason not given | Schematic "Renesas RZ/V2N SOM Board" merged
9 | Internal | RFSoC SOM | Rajesh | S1 Schematic | On Hold | Not added | No date set | 0 | 4 | 0% |  | On Hold |  |  |  |  | On Hold |  |  |  |  | On Hold |  |  |  |  | On Hold |  |  |  |  | NA |  |  |  |  | NA |  |  |  |  | NA | [8 empty] | Reason not given
10 | Qernel.AI | Waimea Validation Board | Kranthi | S1 Schematic | Not Started | Not added | No date set | 0 | 5 | 0% |  | Not Started |  |  | SoW in progress. Waiting for the inputs from customer | Srinivas | Not Started |  |  |  |  | Not Started |  |  |  |  | Not Started |  |  |  |  | Not Started |  |  |  |  | NA |  |  |  |  | NA
11 | RCI | HRG_Processor_Test_Jig | Srinivas L | S1 Schematic | Not Started | Not added | No date set | 0 | 5 | 0% |  | Not Started |  |  | Schematic in progress | Keerthi | Not Started | 2026-09-11 |  |  |  | Not Started |  |  |  |  | Not Started |  |  |  |  | Not Started |  |  |  |  | NA |  |  |  |  | NA
12 | RCI | ITS Boards Refresh | Srinivas L | S1 Schematic | Not Started | Not added | No date set | 0 | 5 | 0% |  | Not Started |  |  | To be started |  | Not Started |  |  |  |  | Not Started |  |  |  |  | Not Started |  |  |  |  | Not Started |  |  |  |  | NA |  |  |  |  | NA
13 | TRS | Handheld RadioCard | V Rajesh | S5 Assembly | In Progress | Not added | No date set | 4 | 5 | 80% | Vardhan | Completed | 2026-09-02 |  |  | Ramesh | Completed | 2026-08-14 |  |  |  | Completed |  |  |  | JLC | Completed |  |  |  |  | In Progress |  |  | PCB Assembly in progress |  | NA |  |  |  |  | NA
14 | TRS | Radio Card 9002 | V Rajesh | S3 SI & PI | In Progress | Not added | No date set | 2 | 5 | 40% |  | Completed |  |  |  | Ramesh | Completed | 2026-08-17 |  |  |  | In Progress |  |  | The design has been completed, the quotation Gerber released, and the simulations are currently in progress. |  | Not Started |  |  |  |  | Not Started |  |  |  |  | NA |  |  |  |  | NA
15 | TRS | Radio Card Lite Ver3 | Rajesh | S2 PCB Layout | On Hold | Not added | No date set | 1 | 5 | 20% | Vardhan | Completed | 2026-08-20 |  |  |  | On Hold |  |  | In Hold |  | On Hold |  |  |  |  | On Hold |  |  |  |  | On Hold |  |  |  |  | NA |  |  |  |  | NA | [8 empty] | Reason not given
16 | TRS | Radio Card Ver4 | Rajesh | S5 Assembly | In Progress | Not added | No date set | 4 | 5 | 80% | Vardhan | Completed | 2026-07-03 |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | In Progress |  |  | Boards In Assembly |  | NA |  |  |  |  | NA
17 | TRS | RC5243(V2) | Rajesh | S5 Assembly | In Progress | Not added | No date set | 4 | 5 | 80% | Vardhan | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | In Progress |  |  | Waiting for BOM |  | NA |  |  |  |  | NA
18 | TRS | SAT-COM Radio Board | V Rajesh | S2 PCB Layout | In Progress | 2026-09-01 | 3 days late | 1 | 5 | 20% |  | Completed |  |  |  | Keerthi | In Progress | 2026-09-01 |  | Routing strategy was revised, SI-based RF path updates were incorporated, and 0201-to-0402 changes were implemented as per assembly requirements, causing a 1-day delay. |  | Not Started |  |  |  |  | Not Started |  |  |  |  | Not Started |  |  |  |  | NA |  |  |  |  | NA | [8 empty] | Reason not given
19 | TRS | SAT-COM_FPGA_Board | Rajesh | S2 PCB Layout | In Progress | 2026-09-04 | 0 days left | 1 | 5 | 20% |  | Completed |  |  |  | Naveen | In Progress | 2026-09-04 |  | Completed the DDR3L S-Parameter extractions. Completed the DC-Drop Analysis and shared the reivew with the layout team waiting for the updated file for simulations. | Vivek | In Progress |  |  |  |  | Not Started |  |  |  |  | Not Started |  |  |  |  | NA |  |  |  |  | NA | [8 empty] | Reason not given | SI&PI row "SAT_COM_FPGA" merged
20 | TRS | Si4464 Proximity Sensor Board | V Rajesh | S2 PCB Layout | In Progress | 2026-09-02 | 2 days late | 1 | 5 | 20% | Vardhan | Completed | 2026-07-21 |  |  | Ramesh | In Progress | 2026-09-02 |  | Design completed. |  | In Progress |  |  |  |  | Not Started |  |  |  |  | Not Started |  |  |  |  | NA |  |  |  |  | NA | [8 empty] | Reason not given | Schematic "PROXIMITY SI4464" merged
21 | Voila Tech | HAWK Board | Rajesh | S6 Bring-up | In Progress | Not added | No date set | 5 | 6 | 83.33% | Vardhan + Sandhya | Completed | 2026-08-20 |  |  | Keerthi | Completed | 2026-07-13 |  |  | Vivek | Completed | 2026-07-14 |  |  | JLC | Completed | 2026-08-19 |  |  |  | Completed |  |  |  |  | In Progress |  |  | Completed the SI simualtions for the SDRAM |  | NA
22 | Voila Tech | Myna Rev 2 | V Rajesh | S4 Bare-PCB Fab | On Hold | Not added | No date set | 2 | 4 | 50% |  | Completed |  |  |  | Naveen | Completed |  |  |  |  | NA |  |  |  |  | On Hold |  |  | The design is complete. The STEP and schematic PDF files have been shared with the client. We are now waiting for their feedback |  | On Hold |  |  |  |  | NA |  |  |  |  | NA | [8 empty] | Reason not given
23 | ZMD | Intel Arrow Island Board | Kiran | S7 BOM Procurement | In Progress | Not added | No date set | 0 | 1 | 0% | Samudra + Sandhya | NA | 2026-08-08 |  |  | Sunil | NA |  |  |  |  | NA |  |  |  |  | NA |  |  |  |  | NA |  |  |  |  | NA |  |  |  |  | In Progress |  |  | To be started | [6 empty] | Blank on upload, set to NA: S6 Assembly. Confirm NA vs Not Started. ¦ Schematic row is BOM sourcing for this board
24 | ZMD | Intel XEON Server Board | Kiran | S2 PCB Layout | Not Started | Not added | No date set | 1 | 5 | 20% | Vardhan + Rajesh Sir | Completed | 2026-08-20 |  |  | Srinivas | Not Started |  |  | To be started |  | Not Started |  |  |  |  | Not Started |  |  |  |  | Not Started |  |  |  |  | NA |  |  |  |  | NA | [9 empty] | Schematic row is BOM sourcing for this board
25 | ZMD | NXP_SOM | Rajesh | S3 SI & PI | In Progress | 2026-08-01 | 34 days late | 1 | 4 | 25% |  | Completed |  |  |  |  | NA |  |  |  | Vivek | In Progress | 2026-08-01 |  | Completed the DC Drop Analysis and LPDDR Inteface s-parameter extraction read and write operations. Waiting for the update layout for the further simulations |  | Not Started |  |  |  |  | Not Started |  |  |  |  | NA |  |  |  |  | NA | [8 empty] | Reason not given | Blank on upload, set to NA: S3 PCB. Confirm NA vs Not Started.
Formulas:
Days = IF([Board]="","",IF(OR([Raised On]="Completed",[Raised On]="Cancelled"),"",IF(NOT(ISNUMBER([Pull in and start at])),"No date set",IF(TODAY()>[Pull in and start at],TODAY()-[Pull in and start at]&" days late",[Pull in and start at]-TODAY()&" days left"))))

## COMPLETED
COMPLETED BOARDS
Boards where every stage is Completed or NA. You can leave this empty — the dashboard moves boards here as they close. Set Respin Needed? = Yes with a Re-entry Stage to send one back.
PROJECT |  |  |  | PROCESS ROLL-UP | [6 empty] | S1 SCHEMATIC |  |  |  |  | S2 PCB LAYOUT |  |  |  |  | S3 SI & PI |  |  |  |  | S4 BARE-PCB FAB |  |  |  |  | S5 ASSEMBLY |  |  |  |  | S6 BRING-UP |  |  |  |  | S7 BOM PROCUREMENT |  |  |  |  | RESPIN CONTROL | [5 empty] | FOLLOW-UP
S.No | Customer | Project / Board | Project Manager | Current Stage | Overall Status | EDC (current stage) | Days | Stages Done | Stages In Scope | % Complete | Owner | Status | EDC | EDA | Comment | Owner | Status | EDC | EDA | Comment | Owner | Status | EDC | EDA | Comment | Fabricator | Status | EDC | EDA | Comment | Owner | Status | EDC | EDA | Comment | Owner | Status | EDC | EDA | Comment | Owner | Status | EDC | EDA | Comment | Respin Needed? | Re-entry Stage | Respin Reason | Raised On | ACTION | # | Hold / delay reason | Reason check | Notes / Data Check
1 | Aerx Labs | DRVU_Mother_Board | Rajesh | All Stages Closed | Completed |  |  | 1 | 1 | 100% |  | NA |  |  |  |  | NA |  |  |  | Vivek | Completed | 2026-07-06 |  |  |  | NA |  |  |  |  | NA |  |  |  |  | NA |  |  |  |  | NA |  |  | SI&PI analysis completed shared with the customer | No
2 | Aerx Labs | PVCC_Board | Rajessh | All Stages Closed | Completed |  |  | 1 | 1 | 100% |  | NA |  |  |  |  | NA |  |  |  | Vivek | Completed | 2026-07-10 |  |  |  | NA |  |  |  |  | NA |  |  |  |  | NA |  |  |  |  | NA |  |  | Completed the SI & PI analysis and shared the report witht the customer | No
3 | FLC | Hardware Validation(FLC) | Rajesh | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Veeresh + Samudra | Completed |  |  |  | Veeresh + Samudra | Completed |  |  |  | Vivek | Completed |  |  |  | Sunil | Completed |  |  |  | Anji | Completed |  |  |  |  | NA |  |  |  |  | NA |  |  |  | No
4 | FLC | MKB_LITE_VALIDATION_V1 | Rajesh | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Veeresh + Samudra | Completed |  |  |  | Veeresh + Samudra | Completed |  |  |  | Vivek | Completed |  |  |  | Sunil | Completed |  |  |  | Anji | Completed |  |  |  |  | NA |  |  |  |  | NA |  |  | Performed the Partial SI and shared the reports. Later, after release, performed the SI & PI to find the issues for the DDR Inteface, PCIE Interface & Power Rails. | No
5 | FLC | MKB_LITE_VALIDATION_V2 | Rajesh | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Veeresh + Samudra | Completed | 2026-05-07 |  |  | Veeresh + Samudra | Completed |  |  |  | Vivek | Completed |  |  |  | Sunil | Completed |  |  |  | Anji | Completed |  |  |  |  | NA |  |  |  |  | NA |  |  | Completed the SI & PI and shared the reports. Performed the SI & PI for the DDR, PCIE_RC , PCIE_EPand DC_DROP and AC anlaysis. | No
6 | GMR | StationIs Rev1 | Srinivas | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Vardhan | Completed | 2026-08-20 |  |  | Keerthi | Completed |  |  |  | Vivek | Completed |  |  |  | Sunil | Completed |  |  |  | Anji | Completed |  |  |  |  | NA |  |  |  |  | NA |  |  | Delivered | No
7 | GMR | StationIs Rev2 | Srinivas | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Vardhan | Completed | 2026-08-20 |  |  | Keerthi | Completed |  |  |  | NA | Completed |  |  |  | Sunil | Completed |  |  |  | Anji | Completed |  |  |  |  | NA |  |  |  |  | NA |  |  | Delivered | No
8 | GMR | StationIs Rev3 | Srinivas | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Vardhan | Completed | 2026-08-20 |  |  | Keerthi | Completed |  |  |  | NA | Completed |  |  |  | Sunil | Completed |  |  |  | Anji | Completed |  |  |  |  | NA |  |  |  |  | NA |  |  |  | No
9 | HAL | HAL_PCB_RE | Rajesh | All Stages Closed | Completed |  |  | 1 | 1 | 100% |  | NA |  |  |  | Vivek | Completed | 2026-08-20 |  |  |  | NA |  |  |  |  | NA |  |  |  |  | NA |  |  |  |  | NA |  |  |  |  | NA |  |  | Anji | No | [7 empty] | Completed
10 | HAL | IFF_BACKLIGHT_ILLUMINATION_BOARD. | Srinivas L | All Stages Closed | Completed |  |  | 1 | 1 | 100% |  | NA |  |  |  | Naveen | Completed | 2026-08-07 |  |  |  | NA |  |  |  |  | NA |  |  |  |  | NA |  |  |  |  | NA |  |  |  |  | NA |  |  | Design completed, waiting for the customer feedback. | No
11 | Internal | NETRA_BASE_BOARD | Rajesh | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Harika | Completed | 2026-06-25 |  |  | Sunil | Completed | 2026-07-05 |  |  | Vivek | Completed | 2026-07-06 |  |  | JLC | Completed | 2026-07-15 |  |  |  | Completed |  |  |  |  | NA |  |  |  |  | NA |  |  | Completed the DC Drop Analysis with JLC PCB Stackup. Completed the S-parameter extraction observed the severe impedance variation, return loss, NEXT, FEXT issues. Due to the connector | No
12 | Internal | Netra_Camera-Board_IMX463&IMX662 | Prithvi | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Harika | Completed |  |  |  | Srinivas | Completed | 2026-07-06 |  |  | Vivek | Completed |  |  |  | Sunil | Completed |  |  |  | Anji | Completed |  |  |  |  | NA |  |  |  |  | NA |  |  | Pcb's Recevied | No | [7 empty] | REVIEW: PCB row covers IMX463+IMX662 combined; schematic/fab rows are per-sensor
13 | Internal | Netra_Camera_ADDON | Rajesh | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Harika | Completed |  |  |  | Srinivas | Completed |  |  |  | Vivek | Completed |  |  |  | Sunil | Completed |  |  |  | Anji | Completed |  |  |  |  | NA |  |  |  |  | NA |  |  | Completed the S-parameter extraction observed the severe impedance variation, return loss, NEXT, FEXT issues. Due to the connector | No | [7 empty] | REVIEW: SI&PI row does not identify which camera add-on
14 | Internal | Netra_Camera_AddOn_IMX462 | Rajesh | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Harika | Completed | 2026-06-30 |  |  | Srinivas | Completed |  |  |  | Vivek | Completed |  |  |  | Sunil | Completed |  |  |  | Anji | Completed |  |  |  |  | NA |  |  |  |  | NA |  |  |  | No
15 | Internal | Netra_Camera_AddOn_IMX662 | Rajesh | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Harika | Completed | 2026-06-30 |  |  | Srinivas | Completed |  |  |  | Vivek | Completed |  |  |  | Sunil | Completed |  |  |  | Anji | Completed |  |  |  |  | NA |  |  |  |  | NA |  |  |  | No
16 | Internal | Netra_LDR-Board | Prithvi | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Harika | Completed | 2026-06-29 |  |  | Srinivas | Completed |  |  |  | Vivek | Completed |  |  |  | Pcb Power | Completed | 2026-07-10 |  |  | Anji | Completed |  |  |  |  | NA |  |  |  |  | NA |  |  | Pcb's Recevied | No | [7 empty] | Schematic row "NETRA_LDR-IR" merged here
17 | Internal | Netra_POE-Board | Prithvi | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Harika | Completed | 2026-06-26 |  |  | Srinivas | Completed |  |  |  | Vivek | Completed |  |  |  | Pcb Power | Completed | 2026-07-10 |  |  | Anji | Completed |  |  |  |  | NA |  |  |  |  | NA |  |  | Pcb's Recevied | No | [7 empty] | Schematic "NETRA_POE" merged here
18 | Internal | Netra_POE_MP8007 | Prithvi | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Harika | Completed |  |  |  | Srinivas | Completed |  |  |  | Vivek | Completed |  |  |  | Sunil | Completed |  |  |  | Anji | Completed |  |  |  |  | NA |  |  |  |  | NA |  |  | Project completed | No
19 | Internal | Netra_SD_Board | Prithvi | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Harika | Completed | 2026-06-30 |  |  | Srinivas | Completed | 2026-07-06 |  |  | Vivek | Completed |  |  |  | Pcb Power | Completed | 2026-07-10 |  |  | Anji | Completed |  |  |  |  | NA |  |  |  |  | NA |  |  | Pcb's Recevied | No | [7 empty] | Schematic "NETRA_SD CARD" + fab "Netra_SD_Card_Board" merged
20 | Internal | RZV2N_Addon_Card | Rajesh | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Veeresh | Completed | 2026-06-18 |  |  | Naveen | Completed | 2026-06-26 |  |  | Vivek | Completed | 2026-06-28 |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | NA |  |  |  |  | NA |  |  | Completed the SI Analysis for the Camera on card. | No
21 | Qernel.AI | Waimea Test Chip Package | Kranthi | All Stages Closed | Cancelled |  |  | 0 | 5 | 0% |  | Cancelled |  |  |  | Srinivas | Cancelled |  |  |  |  | Cancelled |  |  |  |  | Cancelled |  |  |  |  | Cancelled |  |  |  |  | NA |  |  |  |  | NA |  |  | Net list creation in progress. | No
22 | RCI | RCI_BOM | Srinivas | All Stages Closed | Completed |  |  | 1 | 1 | 100% |  | NA |  |  |  |  | NA |  |  |  |  | NA |  |  |  |  | NA |  |  |  |  | NA |  |  |  |  | NA |  |  |  |  | Completed |  |  |  | No
23 | TRS | AX5243 Proximity Sensor Board | V Rajesh | All Stages Closed | Completed |  |  | 2 | 2 | 100% | Vardhan | Completed |  |  |  | Keerthi | Completed | 2026-08-11 |  |  |  | NA |  |  |  |  | NA |  |  |  |  | NA |  |  |  |  | NA |  |  |  |  | NA |  |  | Project completed | No | [7 empty] | Blank on upload, set to NA: S4 SI&PI, S5 Fab, S6 Assembly. Confirm NA vs Not Started. ¦ Schematic "Proximity AX5243" merged
24 | TRS | Radio Card | Rajesh | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Vardhan | Completed | 2026-08-20 |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | NA |  |  |  |  | NA |  |  |  | No
25 | TRS | Radio Card Lite | Rajesh | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Vardhan | Completed | 2026-08-20 |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | NA |  |  |  |  | NA |  |  |  | No
26 | TRS | Radio Card Lite Pro | Rajesh | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Vardhan | Completed | 2026-08-20 |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | NA |  |  |  |  | NA |  |  |  | No
27 | TRS | Radio Card Lite Ver2 | Rajesh | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Vardhan | Completed | 2026-08-20 |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | NA |  |  |  |  | NA |  |  | Delivered | No
28 | TRS | Radio Card Ver2 | Rajesh | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Vardhan | Completed | 2026-08-20 |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | NA |  |  |  |  | NA |  |  |  | No
29 | TRS | Radio Card Ver3 | Rajesh | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Vardhan | Completed | 2026-08-20 |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | NA |  |  |  |  | NA |  |  | Delivered | No
30 | TRS | RC5243 Board | V Rajesh | All Stages Closed | Completed |  |  | 3 | 3 | 100% | Vardhan | Completed | 2026-08-20 |  |  | Keerthi | Completed | 2026-05-22 |  |  |  | NA |  |  |  | Micropack | Completed | 2026-08-26 |  |  |  | NA |  |  |  |  | NA |  |  |  |  | NA |  |  | In Fabrication | No | [7 empty] | Blank on upload, set to NA: S4 SI&PI, S6 Assembly. Confirm NA vs Not Started. ¦ Schematic "RC5243" merged
31 | Unassigned | Proximity_Sensor_Board |  | All Stages Closed | Completed |  |  | 5 | 5 | 100% |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  | JLC | Completed | 2026-08-21 |  |  |  | Completed |  |  |  |  | NA |  |  |  |  | NA |  |  |  | No | [7 empty] | REVIEW: fab order does not say SI4464 or AX5243
32 | Unassigned | USB_Radio-Card |  | All Stages Closed | Completed |  |  | 6 | 6 | 100% |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  | JLC | Completed | 2026-08-18 |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | NA |  |  |  | Yes |  |  |  | SELECT RE-ENTRY STAGE | 1 |  |  | Team flagged "Need to respin" against bring-up
33 | Voila Tech | 8329 BLDC Motor Driver Board | Rajesh | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Vardhan | Completed | 2026-08-20 |  |  |  | Completed |  |  |  |  | Completed |  |  |  | Pcb Power | Completed | 2026-07-12 |  |  |  | Completed |  |  |  |  | NA |  |  |  |  | NA |  |  | Delivered | No | [7 empty] | S4 recorded as "Only PI" - PI done, SI not performed. Confirm scope. ¦ Schematic "8329 BLDC..." + fab order merged
34 | Voila Tech | HAWK Auxiliary Board | V Rajesh | All Stages Closed | Completed |  |  | 4 | 4 | 100% | Vardhan + Sandhya | Completed | 2026-08-20 |  |  | Naveen | Completed | 2026-06-12 |  |  |  | NA |  |  |  | Pcb Power | Completed | 2026-07-14 |  |  |  | Completed |  |  |  |  | NA |  |  |  |  | NA |  |  | Project completed | No
35 | Voila Tech | Magnetic Stirrer | Rajesh | All Stages Closed | Completed |  |  | 2 | 2 | 100% | Vardhan | Completed | 2026-08-20 |  |  |  | Completed |  |  |  |  | NA |  |  |  |  | NA |  |  |  |  | NA |  |  |  |  | NA |  |  |  |  | NA |  |  | Delivered | No
36 | Voila Tech | Myna Board | Rajesh | All Stages Closed | Completed |  |  | 4 | 4 | 100% | Vardhan | Completed | 2026-08-20 |  |  |  | Completed |  |  |  |  | NA |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | NA |  |  |  |  | NA |  |  | Delivered | No
37 | Voila Tech | OverHead Stirrer | Rajesh | All Stages Closed | Completed |  |  | 2 | 2 | 100% | Vardhan + Sandhya | Completed | 2026-08-20 |  |  |  | Completed |  |  |  |  | NA |  |  |  |  | NA |  |  |  |  | NA |  |  |  |  | NA |  |  |  |  | NA |  |  | Delivered | No
38 | Voila Tech | Peptide Synthesizer | Rajesh | All Stages Closed | Completed |  |  | 2 | 2 | 100% | Vardhan | Completed | 2026-08-20 |  |  |  | Completed |  |  |  |  | NA |  |  |  |  | NA |  |  |  |  | NA |  |  |  |  | NA |  |  |  |  | NA |  |  | Delivered | No
39 | Voila Tech | Pilot Evaporator | Rajesh | All Stages Closed | Completed |  |  | 4 | 4 | 100% | Vardhan | Completed | 2026-08-20 |  |  |  | Completed |  |  |  |  | NA |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | NA |  |  |  |  | NA |  |  | Delivered | No
40 | Voila Tech | Rotary Evaporator | Rajesh | All Stages Closed | Completed |  |  | 4 | 4 | 100% | Vardhan | Completed | 2026-08-20 |  |  |  | Completed |  |  |  |  | NA |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | NA |  |  |  |  | NA |  |  | Delivered | No
41 | Voila Tech | Swan Board | V Rajesh | All Stages Closed | Completed |  |  | 4 | 4 | 100% | Vardhan | Completed | 2026-08-20 |  |  | Keerthi | Completed | 2026-07-16 |  |  |  | NA |  |  |  | Pcb Power | Completed | 2026-07-30 |  |  |  | Completed |  |  |  |  | NA |  |  |  |  | NA |  |  | Project completed | No
42 | Voila Tech | Swift Board | V Rajesh | All Stages Closed | Completed |  |  | 4 | 4 | 100% | Vardhan | Completed | 2026-08-20 |  |  | Naveen | Completed | 2026-07-15 |  |  |  | NA |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | NA |  |  |  |  | NA |  |  | Project completed | No
Formulas:
Days = IF([Project / Board]="","",IF(OR([Overall Status]="Completed",[Overall Status]="Cancelled"),"",IF(NOT(ISNUMBER([EDC (current stage)])),"No date set",IF(TODAY()>[EDC (current stage)],TODAY()-[EDC (current stage)]&" days late",[EDC (current stage)]-TODAY()&" days left"))))

## LISTS (hidden)
Status | Stage | Respin Reason | Yes/No | Hold / delay reason | Owner | Client
Completed | S1 Schematic | Design defect found at bring-up | Yes | Waiting on customer feedback | Srinivas | TRS
In Progress | S2 PCB Layout | Component obsolete / not sourceable | No | Waiting on component / long-lead part | Sunil | Internal
On Hold | S3 SI & PI | Customer change request |  | De-prioritised for another board | Samudra | Voila Tech
Not Started | S4 Bare-PCB Fab | SI / PI failure |  | Rework after SI/PI review | Anji | Aerx Labs
NA | S5 Assembly | Fabrication defect |  | Waiting on updated schematic | Vivek | FLC
Cancelled | S6 Bring-up | Assembly or footprint error |  | Fab or assembly queue | Veeresh | GMR
| S7 BOM Procurement | Performance not met |  | Owner not available | Ramesh | HAL
|  | Other - see comment |  | Scope or SoW not agreed | Vardhan | RCI
|  |  |  | Other - see comment | Keerthi | ZMD
[5 empty] | Harika | Qernel.AI
[5 empty] | Sandhya | Unassigned
Naveen
Rajesh Sir