## PROCESS DEFINITION
PCB Tracker — backend data model
Seven stages, four columns each: Owner, Status, EDC, EDA. The dashboard reads and writes these sheets directly.
Stage | Stage name | What happens | Completed when | Owner column holds
S1 | Schematic Design | Requirement capture, part selection, power budget, circuit capture and review. | Schematic released and netlist handed to layout. | A design engineer
S2 | PCB Layout / Design | Stack-up, placement, routing, DFM checks and Gerber release. | DRC/DFM clean and Gerber released. | A layout engineer
S3 | SI & PI Simulation | S-parameter extraction, DC drop, crosstalk, impedance and thermal analysis. | All in-scope interfaces within margin and report shared. | A simulation engineer
S4 | Bare-PCB Fabrication | Bare board ordered and tracked to receipt. | Boards received and inspected. | The fabricator, not a staff member
S5 | Assembly | Component assembly and soldering. | Board populated and inspected. | A hardware engineer
S6 | Bring-up | First power-on, functional validation and debug. | Board validated and handed over. | A hardware engineer
S7 | BOM Procurement | Costing, sourcing and chasing long-lead parts. | Parts sourced or alternates agreed. | A design engineer
Column contract the dashboard depends on
- The field header row must contain a cell reading "Project / Board", with the stage group headers in the row directly above it.
- Each stage group header must keep its name — SCHEMATIC, PCB LAYOUT, SI & PI, BARE-PCB FAB, ASSEMBLY, BRING-UP, BOM PROCUREMENT. The S<n> prefix is ignored, so stages can be renumbered or moved.
- Within a stage block the order is Owner, Status, EDC, EDA. The dashboard detects EDA by its header, so a block without it still works.
- Current Stage, Overall Status, EDC (current stage), Delay, Stages Done, Stages In Scope and % Through Process are formulas. Do not type over them.
- Overall Status alone decides which sheet a board belongs on. The dashboard reads it back after every save and moves the row.
- Owner values must match the "Name in sheet" column on PEOPLE, or the People tab cannot attribute the work. Two people are combined with " + ".
Live roll-up
Stage | Completed | In Progress | On Hold | Not Started | Cancelled | NA
S1 Schematic | 53 | 1 | 2 | 4 | 1 | 6
S2 PCB Layout | 47 | 5 | 3 | 6 | 1 | 5
S3 SI & PI | 31 | 6 | 4 | 9 | 1 | 16
S4 Bare-PCB Fab | 36 | 0 | 5 | 14 | 1 | 11
S5 Assembly | 32 | 3 | 3 | 14 | 1 | 14
S6 Bring-up | 1 | 1 | 0 | 0 | 0 | 65
S7 BOM Procurement | 1 | 1 | 0 | 0 | 0 | 65

## LISTS (hidden)
Status | Re-entry Stage | Respin Reason | Yes/No | Customer | Hold / delay reason | Owner
Completed | S1 Schematic | Design defect found at bring-up | Yes | Aerx Labs | Waiting on customer feedback | Srinivas
In Progress | S2 PCB Layout | Component obsolete / not sourceable | No | FLC | Waiting on component / long-lead part | Sunil
On Hold | S3 SI & PI | Customer change request |  | GMR | De-prioritised for another board | Samudra
Not Started | S4 Bare-PCB Fab | SI / PI failure |  | HAL | Rework after SI/PI review | Anji
NA | S5 Assembly | Fabrication defect |  | Internal | Waiting on updated schematic | Vivek
Cancelled | S6 Bring-up | Assembly or footprint error |  | Not set | Fab or assembly queue | Veeresh
| S7 BOM Procurement | Performance not met |  | Qernel.AI | Owner not available | Ramesh
|  | Other - see comment |  | RCI | Scope or SoW not agreed | Vardhan
|  |  |  | TRS | Other - see comment | Keerthi
|  |  |  | Voila Tech |  | Harika
|  |  |  | ZMD |  | Sandhya
Naveen
Rajesh Sir
PCB Power
JLC
Micropack

## PEOPLE
Hardware team
The dashboard joins stage owners to people through the "Name in sheet" column. A stage owner cell may combine two people with a "+", and each part is matched here.
Employee code | Name | Function | Experience (yrs) | Billing | Projects | Plan | Billed in | Name in sheet
| Srinivasa Rao Supuri | Hardware | 14 | Billed | FLC | Belly Camera | Belly Cam | Srinivas
VC_124 | Galipothu Sunil Kumar | Hardware | 18 | Billed | FLC + TRS + Smart IP Camera | Smart IP Camera, PVC Card |  | Sunil
VC_176 | Jampani Samudralankaiah | Hardware | 6.4 | Billed | FLC + Smart IP Camera + AI Edge Server + RCI ITS | Belly Camera, ZMD Edge | Belly Cam, FLC | Samudra
VC_183 | Varimadla Anjaneyulu | Hardware | 8.1 | Billed | FLC + TRS + Internal / Web + RCI ITS | Support to all Projects |  | Anji
VC_224 | Chintha Vivek Sai | Hardware | 0.1 | Billed | FLC + TRS + Smart IP Camera | need to discuss in August | Belly Cam | Vivek
VC_161 | Veeresh Meeniga | Hardware | 2.7 | Billed | FLC + RCI ITS + RFSOC | need to discuss in Nov | RCI | Veeresh
VC_141 | Ravada Ramesh | Hardware | 4.2 | Billed | TRS | need to discuss in August |  | Ramesh
VC_163 | Ruka Nandi Vardhan Reddy | Hardware | 2.7 | Billed | TRS + Voila Tech + AI Edge Server | need to discuss in August |  | Vardhan
VC_196 | Keerthi Sepana | Hardware | 1.3 | Billed | TRS + Voila Tech | need to discuss in August |  | Keerthi
VC_200 | Harika Kunduru | Hardware | 4 | Billed | Smart IP Camera | Smart IP Camera |  | Harika
VC_229 | Bommi Sandhya | Hardware | [5 empty] | Sandhya
| Naveen | Hardware | [5 empty] | Naveen
| Rajesh | Hardware | [5 empty] | Rajesh Sir
Fabrication vendors
PCB Power | vendor, not counted as workload
JLC | vendor, not counted as workload
Micropack | vendor, not counted as workload

## COMPLETED
COMPLETED BOARDS
Every stage is Completed or NA. Set Respin Needed? = Yes and pick a Re-entry Stage to send a board back; the dashboard moves the row for you.
PROJECT |  |  |  | PROCESS ROLL-UP | [6 empty] | S1 SCHEMATIC |  |  |  | S2 PCB LAYOUT |  |  |  | S3 SI & PI |  |  |  | S4 BARE-PCB FAB |  |  |  | S5 ASSEMBLY |  |  |  | S6 BRING-UP |  |  |  | S7 BOM PROCUREMENT |  |  |  | RESPIN CONTROL (set these to send a board back to ACTIVE) | [5 empty] | FOLLOW-UP
S.No | Customer | Project / Board | Project Manager | Current Stage | Overall Status | EDC (current stage) | Delay (days) | Stages Done | Stages In Scope | % Through Process | Owner | Status | EDC | EDA | Owner | Status | EDC | EDA | Owner | Status | EDC | EDA | Fabricator | Status | EDC | EDA | Owner | Status | EDC | EDA | Owner | Status | EDC | EDA | Owner | Status | EDC | EDA | Respin Needed? | Re-entry Stage | Respin Reason | Raised On | ACTION | # | Hold / delay reason | Reason check | Latest Comment | Notes / Data Check
1 | Aerx Labs | DRVU_Mother_Board | Rajesh | All Stages Closed | Completed |  |  | 1 | 1 | 100% |  | NA |  |  |  | NA |  |  | Vivek | Completed | 2026-07-06 |  |  | NA |  |  |  | NA |  |  |  | NA |  |  |  | NA |  |  | No | [7 empty] | SI&PI analysis completed shared with the customer
2 | Aerx Labs | PVCC_Board | Rajessh | All Stages Closed | Completed |  |  | 1 | 1 | 100% |  | NA |  |  |  | NA |  |  | Vivek | Completed | 2026-07-10 |  |  | NA |  |  |  | NA |  |  |  | NA |  |  |  | NA |  |  | No | [7 empty] | Completed the SI & PI analysis and shared the report witht the customer
3 | FLC | Hardware Validation(FLC) | Rajesh | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Veeresh + Samudra | Completed |  |  | Veeresh + Samudra | Completed |  |  | Vivek | Completed |  |  | Sunil | Completed |  |  | Anji | Completed |  |  |  | NA |  |  |  | NA |  |  | No
4 | FLC | MKB_LITE_VALIDATION_V1 | Rajesh | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Veeresh + Samudra | Completed |  |  | Veeresh + Samudra | Completed |  |  | Vivek | Completed |  |  | Sunil | Completed |  |  | Anji | Completed |  |  |  | NA |  |  |  | NA |  |  | No | [7 empty] | Performed the Partial SI and shared the reports. Later, after release, performed the SI & PI to find the issues for the DDR Inteface, PCIE Interface & Power Rails.
5 | FLC | MKB_LITE_VALIDATION_V2 | Rajesh | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Veeresh + Samudra | Completed | 2026-05-07 |  | Veeresh + Samudra | Completed |  |  | Vivek | Completed |  |  | Sunil | Completed |  |  | Anji | Completed |  |  |  | NA |  |  |  | NA |  |  | No | [7 empty] | Completed the SI & PI and shared the reports. Performed the SI & PI for the DDR, PCIE_RC , PCIE_EPand DC_DROP and AC anlaysis.
6 | GMR | StationIs Rev1 | Srinivas | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Vardhan | Completed | 2026-08-20 |  | Keerthi | Completed |  |  | Vivek | Completed |  |  | Sunil | Completed |  |  | Anji | Completed |  |  |  | NA |  |  |  | NA |  |  | No | [7 empty] | Delivered
7 | GMR | StationIs Rev2 | Srinivas | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Vardhan | Completed | 2026-08-20 |  | Keerthi | Completed |  |  | NA | Completed |  |  | Sunil | Completed |  |  | Anji | Completed |  |  |  | NA |  |  |  | NA |  |  | No | [7 empty] | Delivered
8 | GMR | StationIs Rev3 | Srinivas | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Vardhan | Completed | 2026-08-20 |  | Keerthi | Completed |  |  | NA | Completed |  |  | Sunil | Completed |  |  | Anji | Completed |  |  |  | NA |  |  |  | NA |  |  | No
9 | HAL | HAL_PCB_RE | Rajesh | All Stages Closed | Completed |  |  | 1 | 1 | 100% |  | NA |  |  | Vivek | Completed | 2026-08-20 |  |  | NA |  |  |  | NA |  |  |  | NA |  |  |  | NA |  |  |  | NA |  |  | No | [7 empty] | Anji | Completed
10 | HAL | IFF_BACKLIGHT_ILLUMINATION_BOARD. | Srinivas L | All Stages Closed | Completed |  |  | 1 | 1 | 100% |  | NA |  |  | Naveen | Completed | 2026-08-07 |  |  | NA |  |  |  | NA |  |  |  | NA |  |  |  | NA |  |  |  | NA |  |  | No | [7 empty] | Design completed, waiting for the customer feedback.
11 | Internal | NETRA_BASE_BOARD | Rajesh | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Harika | Completed | 2026-06-25 |  | Sunil | Completed | 2026-07-05 |  | Vivek | Completed | 2026-07-06 |  | JLC | Completed | 2026-07-15 |  |  | Completed |  |  |  | NA |  |  |  | NA |  |  | No | [7 empty] | Completed the DC Drop Analysis with JLC PCB Stackup. Completed the S-parameter extraction observed the severe impedance variation, return loss, NEXT, FEXT issues. Due to the connector
12 | Internal | Netra_Camera-Board_IMX463&IMX662 | Prithvi | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Harika | Completed |  |  | Srinivas | Completed | 2026-07-06 |  | Vivek | Completed |  |  | Sunil | Completed |  |  | Anji | Completed |  |  |  | NA |  |  |  | NA |  |  | No | [7 empty] | Pcb's Recevied | REVIEW: PCB row covers IMX463+IMX662 combined; schematic/fab rows are per-sensor
13 | Internal | Netra_Camera_ADDON | Rajesh | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Harika | Completed |  |  | Srinivas | Completed |  |  | Vivek | Completed |  |  | Sunil | Completed |  |  | Anji | Completed |  |  |  | NA |  |  |  | NA |  |  | No | [7 empty] | Completed the S-parameter extraction observed the severe impedance variation, return loss, NEXT, FEXT issues. Due to the connector | REVIEW: SI&PI row does not identify which camera add-on
14 | Internal | Netra_Camera_AddOn_IMX462 | Rajesh | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Harika | Completed | 2026-06-30 |  | Srinivas | Completed |  |  | Vivek | Completed |  |  | Sunil | Completed |  |  | Anji | Completed |  |  |  | NA |  |  |  | NA |  |  | No
15 | Internal | Netra_Camera_AddOn_IMX662 | Rajesh | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Harika | Completed | 2026-06-30 |  | Srinivas | Completed |  |  | Vivek | Completed |  |  | Sunil | Completed |  |  | Anji | Completed |  |  |  | NA |  |  |  | NA |  |  | No
16 | Internal | Netra_LDR-Board | Prithvi | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Harika | Completed | 2026-06-29 |  | Srinivas | Completed |  |  | Vivek | Completed |  |  | Pcb Power | Completed | 2026-07-10 |  | Anji | Completed |  |  |  | NA |  |  |  | NA |  |  | No | [7 empty] | Pcb's Recevied | Schematic row "NETRA_LDR-IR" merged here
17 | Internal | Netra_POE-Board | Prithvi | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Harika | Completed | 2026-06-26 |  | Srinivas | Completed |  |  | Vivek | Completed |  |  | Pcb Power | Completed | 2026-07-10 |  | Anji | Completed |  |  |  | NA |  |  |  | NA |  |  | No | [7 empty] | Pcb's Recevied | Schematic "NETRA_POE" merged here
18 | Internal | Netra_POE_MP8007 | Prithvi | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Harika | Completed |  |  | Srinivas | Completed |  |  | Vivek | Completed |  |  | Sunil | Completed |  |  | Anji | Completed |  |  |  | NA |  |  |  | NA |  |  | No | [7 empty] | Project completed
19 | Internal | Netra_SD_Board | Prithvi | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Harika | Completed | 2026-06-30 |  | Srinivas | Completed | 2026-07-06 |  | Vivek | Completed |  |  | Pcb Power | Completed | 2026-07-10 |  | Anji | Completed |  |  |  | NA |  |  |  | NA |  |  | No | [7 empty] | Pcb's Recevied | Schematic "NETRA_SD CARD" + fab "Netra_SD_Card_Board" merged
20 | Internal | RZV2N_Addon_Card | Rajesh | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Veeresh | Completed | 2026-06-18 |  | Naveen | Completed | 2026-06-26 |  | Vivek | Completed | 2026-06-28 |  |  | Completed |  |  |  | Completed |  |  |  | NA |  |  |  | NA |  |  | No | [7 empty] | Completed the SI Analysis for the Camera on card.
21 | Not set | Proximity_Sensor_Board |  | All Stages Closed | Completed |  |  | 5 | 5 | 100% |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  | JLC | Completed | 2026-08-21 |  |  | Completed |  |  |  | NA |  |  |  | NA |  |  | No | [8 empty] | REVIEW: fab order does not say SI4464 or AX5243
22 | Not set | USB_Radio-Card |  | All Stages Closed | Completed |  |  | 6 | 6 | 100% |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  | JLC | Completed | 2026-08-18 |  |  | Completed |  |  |  | Completed |  |  |  | NA |  |  | Yes |  |  |  | SELECT RE-ENTRY STAGE | 1 |  |  |  | Team flagged "Need to respin" against bring-up
23 | Qernel.AI | Waimea Test Chip Package | Kranthi | All Stages Closed | Cancelled |  |  | 0 | 5 | 0% |  | Cancelled |  |  | Srinivas | Cancelled |  |  |  | Cancelled |  |  |  | Cancelled |  |  |  | Cancelled |  |  |  | NA |  |  |  | NA |  |  | No | [7 empty] | Net list creation in progress.
24 | RCI | RCI_BOM | Srinivas | All Stages Closed | Completed |  |  | 1 | 1 | 100% |  | NA |  |  |  | NA |  |  |  | NA |  |  |  | NA |  |  |  | NA |  |  |  | NA |  |  |  | Completed |  |  | No
25 | TRS | AX5243 Proximity Sensor Board | V Rajesh | All Stages Closed | Completed |  |  | 2 | 2 | 100% | Vardhan | Completed |  |  | Keerthi | Completed | 2026-08-11 |  |  | NA |  |  |  | NA |  |  |  | NA |  |  |  | NA |  |  |  | NA |  |  | No | [7 empty] | Project completed | Blank on upload, set to NA: S4 SI&PI, S5 Fab, S6 Assembly. Confirm NA vs Not Started. ¦ Schematic "Proximity AX5243" merged
26 | TRS | Radio Card | Rajesh | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Vardhan | Completed | 2026-08-20 |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | NA |  |  |  | NA |  |  | No
27 | TRS | Radio Card Lite | Rajesh | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Vardhan | Completed | 2026-08-20 |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | NA |  |  |  | NA |  |  | No
28 | TRS | Radio Card Lite Pro | Rajesh | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Vardhan | Completed | 2026-08-20 |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | NA |  |  |  | NA |  |  | No
29 | TRS | Radio Card Lite Ver2 | Rajesh | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Vardhan | Completed | 2026-08-20 |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | NA |  |  |  | NA |  |  | No | [7 empty] | Delivered
30 | TRS | Radio Card Ver2 | Rajesh | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Vardhan | Completed | 2026-08-20 |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | NA |  |  |  | NA |  |  | No
31 | TRS | Radio Card Ver3 | Rajesh | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Vardhan | Completed | 2026-08-20 |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | NA |  |  |  | NA |  |  | No | [7 empty] | Delivered
32 | TRS | RC5243 Board | V Rajesh | All Stages Closed | Completed |  |  | 3 | 3 | 100% | Vardhan | Completed | 2026-08-20 |  | Keerthi | Completed | 2026-05-22 |  |  | NA |  |  | Micropack | Completed | 2026-08-26 |  |  | NA |  |  |  | NA |  |  |  | NA |  |  | No | [7 empty] | In Fabrication | Blank on upload, set to NA: S4 SI&PI, S6 Assembly. Confirm NA vs Not Started. ¦ Schematic "RC5243" merged
33 | Voila Tech | 8329 BLDC Motor Driver Board | Rajesh | All Stages Closed | Completed |  |  | 5 | 5 | 100% | Vardhan | Completed | 2026-08-20 |  |  | Completed |  |  |  | Completed |  |  | Pcb Power | Completed | 2026-07-12 |  |  | Completed |  |  |  | NA |  |  |  | NA |  |  | No | [7 empty] | Delivered | S4 recorded as "Only PI" - PI done, SI not performed. Confirm scope. ¦ Schematic "8329 BLDC..." + fab order merged
34 | Voila Tech | HAWK Auxiliary Board | V Rajesh | All Stages Closed | Completed |  |  | 4 | 4 | 100% | Vardhan + Sandhya | Completed | 2026-08-20 |  | Naveen | Completed | 2026-06-12 |  |  | NA |  |  | Pcb Power | Completed | 2026-07-14 |  |  | Completed |  |  |  | NA |  |  |  | NA |  |  | No | [7 empty] | Project completed
35 | Voila Tech | Magnetic Stirrer | Rajesh | All Stages Closed | Completed |  |  | 2 | 2 | 100% | Vardhan | Completed | 2026-08-20 |  |  | Completed |  |  |  | NA |  |  |  | NA |  |  |  | NA |  |  |  | NA |  |  |  | NA |  |  | No | [7 empty] | Delivered
36 | Voila Tech | Myna Board | Rajesh | All Stages Closed | Completed |  |  | 4 | 4 | 100% | Vardhan | Completed | 2026-08-20 |  |  | Completed |  |  |  | NA |  |  |  | Completed |  |  |  | Completed |  |  |  | NA |  |  |  | NA |  |  | No | [7 empty] | Delivered
37 | Voila Tech | OverHead Stirrer | Rajesh | All Stages Closed | Completed |  |  | 2 | 2 | 100% | Vardhan + Sandhya | Completed | 2026-08-20 |  |  | Completed |  |  |  | NA |  |  |  | NA |  |  |  | NA |  |  |  | NA |  |  |  | NA |  |  | No | [7 empty] | Delivered
38 | Voila Tech | Peptide Synthesizer | Rajesh | All Stages Closed | Completed |  |  | 2 | 2 | 100% | Vardhan | Completed | 2026-08-20 |  |  | Completed |  |  |  | NA |  |  |  | NA |  |  |  | NA |  |  |  | NA |  |  |  | NA |  |  | No | [7 empty] | Delivered
39 | Voila Tech | Pilot Evaporator | Rajesh | All Stages Closed | Completed |  |  | 4 | 4 | 100% | Vardhan | Completed | 2026-08-20 |  |  | Completed |  |  |  | NA |  |  |  | Completed |  |  |  | Completed |  |  |  | NA |  |  |  | NA |  |  | No | [7 empty] | Delivered
40 | Voila Tech | Rotary Evaporator | Rajesh | All Stages Closed | Completed |  |  | 4 | 4 | 100% | Vardhan | Completed | 2026-08-20 |  |  | Completed |  |  |  | NA |  |  |  | Completed |  |  |  | Completed |  |  |  | NA |  |  |  | NA |  |  | No | [7 empty] | Delivered
41 | Voila Tech | Swan Board | V Rajesh | All Stages Closed | Completed |  |  | 4 | 4 | 100% | Vardhan | Completed | 2026-08-20 |  | Keerthi | Completed | 2026-07-16 |  |  | NA |  |  | Pcb Power | Completed | 2026-07-30 |  |  | Completed |  |  |  | NA |  |  |  | NA |  |  | No | [7 empty] | Project completed
42 | Voila Tech | Swift Board | V Rajesh | All Stages Closed | Completed |  |  | 4 | 4 | 100% | Vardhan | Completed | 2026-08-20 |  | Naveen | Completed | 2026-07-15 |  |  | NA |  |  |  | Completed |  |  |  | Completed |  |  |  | NA |  |  |  | NA |  |  | No | [7 empty] | Project completed
Formulas:
Delay (days) = IF(OR([Overall Status]="Completed",[Overall Status]="Cancelled"),"",IF(NOT(ISNUMBER([EDC (current stage)])),"Date not added",IF(TODAY()>[EDC (current stage)],TODAY()-[EDC (current stage)],[EDC (current stage)]-TODAY()&" days left")))

## ACTIVE
ACTIVE / PENDING BOARDS
RESPIN QUEUE | [6 empty] | 1 board(s) flagged for respin
# | Customer | Board | Re-entry Stage | Respin Reason | Raised On | Pull in and start at
1 | Not set | USB_Radio-Card |  |  |  | Re-entry stage not set
2
3
4
5
6
7
8
PROJECT |  |  |  | PROCESS ROLL-UP | [6 empty] | S1 SCHEMATIC |  |  |  | S2 PCB LAYOUT |  |  |  | S3 SI & PI |  |  |  | S4 BARE-PCB FAB |  |  |  | S5 ASSEMBLY |  |  |  | S6 BRING-UP |  |  |  | S7 BOM PROCUREMENT |  |  |  | RESPIN ORIGIN |  |  |  | FOLLOW-UP
S.No | Customer | Project / Board | Project Manager | Current Stage | Overall Status | EDC (current stage) | Delay (days) | Stages Done | Stages In Scope | % Through Process | Owner | Status | EDC | EDA | Owner | Status | EDC | EDA | Owner | Status | EDC | EDA | Fabricator | Status | EDC | EDA | Owner | Status | EDC | EDA | Owner | Status | EDC | EDA | Owner | Status | EDC | EDA | Rev / Respin No. | Re-entered At | Respin Reason | Raised On | Hold / delay reason | Reason check | Latest Comment | Notes / Data Check
1 | Aerx Labs | Belly Camera | Prithvi | S1 Schematic | In Progress | 2026-09-08 | 5 days left | 0 | 5 | 0% | Samudra | In Progress | 2026-09-08 |  | Srinivas | Not Started |  |  |  | Not Started |  |  |  | Not Started |  |  |  | Not Started |  |  |  | NA |  |  |  | NA | [8 empty] | Schematic in progress
2 | Aerx Labs | PVC_CC_V2 / PVCC_V2 | Rajesh | S3 SI & PI | In Progress | Not added | Date not added | 2 | 3 | 66.67% | Samudra | Completed |  |  | Sunil | Completed | 2026-07-28 |  | Vivek | In Progress |  |  |  | NA |  |  |  | NA |  |  |  | NA |  |  |  | NA | [8 empty] | Received the updated file, completed the simulations shared the review. Crosstalk issues were still there; shared with the layout team for modifications | PCB "PVC_CC_V2" + SI&PI "PVCC_V2_Board" merged
3 | FLC | MKB_LITE_FHHL | Rajesh | S3 SI & PI | On Hold | Not added | Date not added | 2 | 5 | 40% | Veeresh | Completed | 2026-05-15 |  | Veeresh + Samudra | Completed |  |  | Vivek | On Hold |  |  |  | On Hold |  |  |  | On Hold |  |  |  | NA |  |  |  | NA | [7 empty] | Reason not given | Performed the SI & PI for the DDR, PCIe_RC and DC_DROP and AC anlaysis. EP_PCIe Interface is pending due to crosstalk and return loss issues at the edge finger.
4 | HAL | CITAR Module Design | Srinivas L | S1 Schematic | Not Started | Not added | Date not added | 0 | 5 | 0% |  | Not Started |  |  | Ramesh | Not Started | 2026-09-11 |  |  | Not Started |  |  |  | Not Started |  |  |  | Not Started |  |  |  | NA |  |  |  | NA | [8 empty] | Schematic in progress
5 | Internal | NETRA_NT98566_CAMERA_MODULE | Prithvi | S2 PCB Layout | In Progress | 2026-09-13 | 10 days left | 1 | 5 | 20% | Sandhya | Completed |  |  | Sunil | In Progress | 2026-09-13 |  |  | Not Started |  |  |  | Not Started |  |  |  | Not Started |  |  |  | NA |  |  |  | NA | [8 empty] | Component footprint verification in progress
6 | Internal | Netra_NXP_SOM_Board | Prithvi | S3 SI & PI | In Progress | Not added | Date not added | 2 | 5 | 40% | Samudra + Sandhya | Completed | 2026-07-21 |  | Srinivas | Completed | 2026-09-08 |  |  | In Progress |  |  |  | Not Started |  |  |  | Not Started |  |  |  | NA |  |  |  | NA | [8 empty] | Routing completed,Need the updated schematic as per the review modifications. | Schematic row = Compulab replacement variant. SI&PI "NXP_SOM" (ZMD) kept separate — confirm if same board
7 | Internal | Netra_POE_Plus(MP8008) | Prithvi | S1 Schematic | On Hold | Not added | Date not added | 0 | 4 | 0% |  | On Hold |  |  | Naveen | On Hold | 2026-08-19 |  |  | On Hold |  |  |  | On Hold |  |  |  | NA |  |  |  | NA |  |  |  | NA | [7 empty] | Reason not given | ZYNQ Module for RF Camera prioritized | Blank on upload, set to NA: S6 Assembly. Confirm NA vs Not Started.
8 | Internal | Netra_RZ/V2N_SOM (Renesas) | Prithvi | S2 PCB Layout | In Progress | 2026-09-25 | 22 days left | 1 | 5 | 20% | Veeresh + Samudra | Completed | 2026-09-04 |  | Srinivas | In Progress | 2026-09-25 |  |  | Not Started |  |  |  | Not Started |  |  |  | Not Started |  |  |  | NA |  |  |  | NA | [8 empty] | Placement is in progress. The component sizes need to be changed in the schematic. I have informed Veeresh and am waiting for the updated schematic. | Schematic "Renesas RZ/V2N SOM Board" merged
9 | Internal | RFSoC SOM | Rajesh | S1 Schematic | On Hold | Not added | Date not added | 0 | 4 | 0% |  | On Hold |  |  |  | On Hold |  |  |  | On Hold |  |  |  | On Hold |  |  |  | NA |  |  |  | NA |  |  |  | NA | [7 empty] | Reason not given
10 | Qernel.AI | Waimea Validation Board | Kranthi | S1 Schematic | Not Started | Not added | Date not added | 0 | 5 | 0% |  | Not Started |  |  | Srinivas | Not Started |  |  |  | Not Started |  |  |  | Not Started |  |  |  | Not Started |  |  |  | NA |  |  |  | NA | [8 empty] | SoW in progress. Waiting for the inputs from customer
11 | RCI | HRG_Processor_Test_Jig | Srinivas L | S1 Schematic | Not Started | Not added | Date not added | 0 | 5 | 0% |  | Not Started |  |  | Keerthi | Not Started | 2026-09-11 |  |  | Not Started |  |  |  | Not Started |  |  |  | Not Started |  |  |  | NA |  |  |  | NA | [8 empty] | Schematic in progress
12 | RCI | ITS Boards Refresh | Srinivas L | S1 Schematic | Not Started | Not added | Date not added | 0 | 5 | 0% |  | Not Started |  |  |  | Not Started |  |  |  | Not Started |  |  |  | Not Started |  |  |  | Not Started |  |  |  | NA |  |  |  | NA | [8 empty] | To be started
13 | TRS | Handheld RadioCard | V Rajesh | S5 Assembly | In Progress | Not added | Date not added | 4 | 5 | 80% | Vardhan | Completed | 2026-09-02 |  | Ramesh | Completed | 2026-08-14 |  |  | Completed |  |  | JLC | Completed |  |  |  | In Progress |  |  |  | NA |  |  |  | NA | [8 empty] | PCB Assembly in progress
14 | TRS | Radio Card 9002 | V Rajesh | S3 SI & PI | In Progress | Not added | Date not added | 2 | 5 | 40% |  | Completed |  |  | Ramesh | Completed | 2026-08-17 |  |  | In Progress |  |  |  | Not Started |  |  |  | Not Started |  |  |  | NA |  |  |  | NA | [8 empty] | The design has been completed, the quotation Gerber released, and the simulations are currently in progress.
15 | TRS | Radio Card Lite Ver3 | Rajesh | S2 PCB Layout | On Hold | Not added | Date not added | 1 | 5 | 20% | Vardhan | Completed | 2026-08-20 |  |  | On Hold |  |  |  | On Hold |  |  |  | On Hold |  |  |  | On Hold |  |  |  | NA |  |  |  | NA | [7 empty] | Reason not given | In Hold
16 | TRS | Radio Card Ver4 | Rajesh | S5 Assembly | In Progress | Not added | Date not added | 4 | 5 | 80% | Vardhan | Completed | 2026-07-03 |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | In Progress |  |  |  | NA |  |  |  | NA | [8 empty] | Boards In Assembly
17 | TRS | RC5243(V2) | Rajesh | S5 Assembly | In Progress | Not added | Date not added | 4 | 5 | 80% | Vardhan | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | Completed |  |  |  | In Progress |  |  |  | NA |  |  |  | NA | [8 empty] | Waiting for BOM
18 | TRS | SAT-COM Radio Board | V Rajesh | S2 PCB Layout | In Progress | 2026-09-01 | 2 | 1 | 5 | 20% |  | Completed |  |  | Keerthi | In Progress | 2026-09-01 |  |  | Not Started |  |  |  | Not Started |  |  |  | Not Started |  |  |  | NA |  |  |  | NA | [7 empty] | Reason not given | Routing strategy was revised, SI-based RF path updates were incorporated, and 0201-to-0402 changes were implemented as per assembly requirements, causing a 1-day delay.
19 | TRS | SAT-COM_FPGA_Board | Rajesh | S2 PCB Layout | In Progress | 2026-09-04 | 1 days left | 1 | 5 | 20% |  | Completed |  |  | Naveen | In Progress | 2026-09-04 |  | Vivek | In Progress |  |  |  | Not Started |  |  |  | Not Started |  |  |  | NA |  |  |  | NA | [8 empty] | Completed the DDR3L S-Parameter extractions. Completed the DC-Drop Analysis and shared the reivew with the layout team waiting for the updated file for simulations. | SI&PI row "SAT_COM_FPGA" merged
20 | TRS | Si4464 Proximity Sensor Board | V Rajesh | S2 PCB Layout | In Progress | 2026-09-02 | 1 | 1 | 5 | 20% | Vardhan | Completed | 2026-07-21 |  | Ramesh | In Progress | 2026-09-02 |  |  | In Progress |  |  |  | Not Started |  |  |  | Not Started |  |  |  | NA |  |  |  | NA | [7 empty] | Reason not given | Design completed. | Schematic "PROXIMITY SI4464" merged
21 | Voila Tech | HAWK Board | Rajesh | S6 Bring-up | In Progress | Not added | Date not added | 5 | 6 | 83.33% | Vardhan + Sandhya | Completed | 2026-08-20 |  | Keerthi | Completed | 2026-07-13 |  | Vivek | Completed | 2026-07-14 |  | JLC | Completed | 2026-08-19 |  |  | Completed |  |  |  | In Progress |  |  |  | NA | [8 empty] | Completed the SI simualtions for the SDRAM
22 | Voila Tech | Myna Rev 2 | V Rajesh | S4 Bare-PCB Fab | On Hold | Not added | Date not added | 2 | 4 | 50% |  | Completed |  |  | Naveen | Completed |  |  |  | NA |  |  |  | On Hold |  |  |  | On Hold |  |  |  | NA |  |  |  | NA | [7 empty] | Reason not given | The design is complete. The STEP and schematic PDF files have been shared with the client. We are now waiting for their feedback
23 | ZMD | Intel Arrow Island Board | Kiran | S7 BOM Procurement | In Progress | Not added | Date not added | 0 | 1 | 0% | Samudra + Sandhya | NA | 2026-08-08 |  | Sunil | NA |  |  |  | NA |  |  |  | NA |  |  |  | NA |  |  |  | NA |  |  |  | In Progress | [8 empty] | To be started | Blank on upload, set to NA: S6 Assembly. Confirm NA vs Not Started. ¦ Schematic row is BOM sourcing for this board
24 | ZMD | Intel XEON Server Board | Kiran | S2 PCB Layout | Not Started | Not added | Date not added | 1 | 5 | 20% | Vardhan + Rajesh Sir | Completed | 2026-08-20 |  | Srinivas | Not Started |  |  |  | Not Started |  |  |  | Not Started |  |  |  | Not Started |  |  |  | NA |  |  |  | NA | [8 empty] | To be started | Schematic row is BOM sourcing for this board
25 | ZMD | NXP_SOM | Rajesh | S3 SI & PI | In Progress | 2026-08-01 | 33 | 1 | 4 | 25% |  | Completed |  |  |  | NA |  |  | Vivek | In Progress | 2026-08-01 |  |  | Not Started |  |  |  | Not Started |  |  |  | NA |  |  |  | NA | [7 empty] | Reason not given | Completed the DC Drop Analysis and LPDDR Inteface s-parameter extraction read and write operations. Waiting for the update layout for the further simulations | Blank on upload, set to NA: S3 PCB. Confirm NA vs Not Started.
Formulas:
Delay (days) = IF(OR([Raised On]="Completed",[Raised On]="Cancelled"),"",IF(NOT(ISNUMBER([Pull in and start at])),"Date not added",IF(TODAY()>[Pull in and start at],TODAY()-[Pull in and start at],[Pull in and start at]-TODAY()&" days left")))