## START HERE
PCB Tracker — fill these in
Work through the sheets in this order. Everything else is calculated or filled by the dashboard.
| Step | Sheet | What to do
| 1 | CLIENTS | List every customer once. The name you type here is what appears everywhere else, so settle the naming now — change it later and old rows will not match.
| 2 | EMPLOYEES | Your team. The "Name in sheet" column is the short name people actually type as a stage owner. Get this right or the People tab cannot attribute work.
| 3 | LISTS | Statuses, reasons and stage names. Already filled — only edit if you want different wording.
| 4 | ACTIVE | One row per board still in progress. Fill Customer, Board, Manager, then each stage: Owner, Status, EDC. Leave EDA until the stage finishes.
| 5 | COMPLETED | Boards where every stage is done. Same columns. You can leave this empty and let the dashboard move boards here as they close.
| 6 | — | Publish the dashboard. From then on the team fills everything through it and these sheets update themselves.
Rules worth knowing
- Cream-coloured cells are yours to fill. White cells with formulas calculate themselves — do not type over them.
- A stage marked NA is not part of that board. It is hidden from the dashboard and excluded from the completion percentage.
- EDC is the expected date of completion. EDA is the actual one. The dashboard writes EDA when someone presses Review done.
- Overall Status decides which sheet a board belongs on. The dashboard reads it back after every save and moves the row.
- Stage owners may combine two people with " + ", for example "Samudra + Sandhya". Both are matched against EMPLOYEES.

## CLIENTS
Clients
One row per customer. The Client name column feeds every dropdown in the tracker.
| Client name | Short code | Sector / domain | Account owner | Status | Notes

## EMPLOYEES
Employees
Your roster, pre-filled from what you sent. "Name in sheet" is the short name typed into stage Owner cells — it is the join the People tab depends on.
| Employee code | Full name | Function | Experience (yrs) | Billing | Name in sheet | Projects | Plan | Active?
|  | Srinivasa Rao Supuri | Hardware | 14 | Billed | Srinivas |  |  | Yes
| VC_124 | Galipothu Sunil Kumar | Hardware | 18 | Billed | Sunil |  |  | Yes
| VC_176 | Jampani Samudralankaiah | Hardware | 6.4 | Billed | Samudra |  |  | Yes
| VC_183 | Varimadla Anjaneyulu | Hardware | 8.1 | Billed | Anji |  |  | Yes
| VC_224 | Chintha Vivek Sai | Hardware | 0.1 | Billed | Vivek |  |  | Yes
| VC_161 | Veeresh Meeniga | Hardware | 2.7 | Billed | Veeresh |  |  | Yes
| VC_141 | Ravada Ramesh | Hardware | 4.2 | Billed | Ramesh |  |  | Yes
| VC_163 | Ruka Nandi Vardhan Reddy | Hardware | 2.7 | Billed | Vardhan |  |  | Yes
| VC_196 | Keerthi Sepana | Hardware | 1.3 | Billed | Keerthi |  |  | Yes
| VC_200 | Harika Kunduru | Hardware | 4 | Billed | Harika |  |  | Yes
| VC_229 | Bommi Sandhya | Hardware |  |  | Sandhya |  |  | Yes
|  | Naveen | Hardware |  |  | Naveen |  |  | Yes
|  | Rajesh | Hardware |  |  | Rajesh Sir |  |  | Yes
| Fabrication vendors | Listed separately so fab work is never counted as someone's workload.
PCB Power
JLC
Micropack

## PROCESS DEFINITION
Process definition
Seven stages, four columns each: Owner, Status, EDC, EDA.
| Stage | Stage name | Completed when | Owner column holds
| S1 | Schematic Design | Schematic released and netlist handed to layout. | A design engineer
| S2 | PCB Layout / Design | DRC and DFM clean, Gerber released. | A layout engineer
| S3 | SI & PI Simulation | All in-scope interfaces within margin and report shared. | A simulation engineer
| S4 | Bare-PCB Fabrication | Bare boards received and inspected. | The fabricator, not a staff member
| S5 | Assembly | Board populated and inspected. | A hardware engineer
| S6 | Bring-up | Board powers up, passes validation and is handed over. | A hardware engineer
| S7 | BOM Procurement | Parts sourced, or alternates agreed. | A design engineer
Column contract the dashboard depends on
- The field header row must contain "Project / Board", with the stage group headers in the row directly above.
- Each stage group header must keep its name — SCHEMATIC, PCB LAYOUT, SI & PI, BARE-PCB FAB, ASSEMBLY, BRING-UP, BOM PROCUREMENT. The S<n> prefix is ignored.
- Within a stage block the order is Owner, Status, EDC, EDA.
- Owner values must match the "Name in sheet" column on EMPLOYEES. Two people combine with " + ".
- Customer values must match the Client name column on CLIENTS.

## ACTIVE
ACTIVE / PENDING BOARDS
One row per board still in progress. Fill the cream cells; the white ones calculate. EDC is the expected date of completion, EDA the actual one.
RESPIN QUEUE | [6 empty] | 0 board(s) flagged for respin
# | Customer | Board | Re-entry Stage | Respin Reason | Raised On | Pull in and start at
1
2
3
4
5
6
7
8
PROJECT |  |  |  | PROCESS ROLL-UP | [6 empty] | S1 SCHEMATIC |  |  |  |  | S2 PCB LAYOUT |  |  |  |  | S3 SI & PI |  |  |  |  | S4 BARE-PCB FAB |  |  |  |  | S5 ASSEMBLY |  |  |  |  | S6 BRING-UP |  |  |  |  | S7 BOM PROCUREMENT |  |  |  |  | RESPIN ORIGIN |  |  |  | FOLLOW-UP
S.No | Customer | Project / Board | Project Manager | Current Stage | Overall Status | EDC (current stage) | Days | Stages Done | Stages In Scope | % Complete | Owner | Status | EDC | EDA | Comment | Owner | Status | EDC | EDA | Comment | Owner | Status | EDC | EDA | Comment | Fabricator | Status | EDC | EDA | Comment | Owner | Status | EDC | EDA | Comment | Owner | Status | EDC | EDA | Comment | Owner | Status | EDC | EDA | Comment | Rev / Respin No. | Re-entered At | Respin Reason | Raised On | Hold / delay reason | Reason check | Notes / Data Check
Formulas:
Days = IF([Board]="","",IF(OR([Raised On]="Completed",[Raised On]="Cancelled"),"",IF(NOT(ISNUMBER([Pull in and start at])),"No date set",IF(TODAY()>[Pull in and start at],TODAY()-[Pull in and start at]&" days late",[Pull in and start at]-TODAY()&" days left"))))

## COMPLETED
COMPLETED BOARDS
Boards where every stage is Completed or NA. You can leave this empty — the dashboard moves boards here as they close. Set Respin Needed? = Yes with a Re-entry Stage to send one back.
PROJECT |  |  |  | PROCESS ROLL-UP | [6 empty] | S1 SCHEMATIC |  |  |  |  | S2 PCB LAYOUT |  |  |  |  | S3 SI & PI |  |  |  |  | S4 BARE-PCB FAB |  |  |  |  | S5 ASSEMBLY |  |  |  |  | S6 BRING-UP |  |  |  |  | S7 BOM PROCUREMENT |  |  |  |  | RESPIN CONTROL | [5 empty] | FOLLOW-UP
S.No | Customer | Project / Board | Project Manager | Current Stage | Overall Status | EDC (current stage) | Days | Stages Done | Stages In Scope | % Complete | Owner | Status | EDC | EDA | Comment | Owner | Status | EDC | EDA | Comment | Owner | Status | EDC | EDA | Comment | Fabricator | Status | EDC | EDA | Comment | Owner | Status | EDC | EDA | Comment | Owner | Status | EDC | EDA | Comment | Owner | Status | EDC | EDA | Comment | Respin Needed? | Re-entry Stage | Respin Reason | Raised On | ACTION | # | Hold / delay reason | Reason check | Notes / Data Check
Formulas:
Days = IF([Project / Board]="","",IF(OR([Overall Status]="Completed",[Overall Status]="Cancelled"),"",IF(NOT(ISNUMBER([EDC (current stage)])),"No date set",IF(TODAY()>[EDC (current stage)],TODAY()-[EDC (current stage)]&" days late",[EDC (current stage)]-TODAY()&" days left"))))

## LISTS (hidden)
Status | Stage | Respin Reason | Yes/No | Hold / delay reason | Owner | Client
Completed | S1 Schematic | Design defect found at bring-up | Yes | Waiting on customer feedback | Srinivas
In Progress | S2 PCB Layout | Component obsolete / not sourceable | No | Waiting on component / long-lead part | Sunil
On Hold | S3 SI & PI | Customer change request |  | De-prioritised for another board | Samudra
Not Started | S4 Bare-PCB Fab | SI / PI failure |  | Rework after SI/PI review | Anji
NA | S5 Assembly | Fabrication defect |  | Waiting on updated schematic | Vivek
Cancelled | S6 Bring-up | Assembly or footprint error |  | Fab or assembly queue | Veeresh
| S7 BOM Procurement | Performance not met |  | Owner not available | Ramesh
|  | Other - see comment |  | Scope or SoW not agreed | Vardhan
|  |  |  | Other - see comment | Keerthi
Harika
Sandhya
Naveen
Rajesh Sir